# Project Notes - Meeting #2 | Deep Learning Project 10 Group

First draft: Friday, December 12, 2025

Video Film: Wednesday, December 17, 2025

Project aims to be completed by: Friday, December 19, 2025

Project drop dead due date: Monday, December 22, 2025

## Discussion

- Implementing Ensemble with temp scaling (need multiple models to compare against)

- Project completion timeline

- Review report template

## Tasks

- Build basic ResNet Model for Gleason Score classification

- Implement Montecarlo dropout to model training

- Implement temp scaling & Ensemble

- Compile graphs, statistics, and data

- Build report

- Create video showcase

### Implement Monte Carlo Dropout

Assignee: Mike

Todo:

- Research Montecarlo dropout and review implementation steps

- Implement Montecarlo dropout into existing model

- Train model with dropout and get graphs, data, and statistics

- Review uncertainty papers and assist Hermes (https://arxiv.org/abs/1612.01474, https://papers.miccai.org/miccai-2024/811-Paper2652.html)

- Add section to report

### Implement Temp Scaling & Ensemble

Assignee: Hermes

Todo:

- Research temp scaling and review implementation steps

- Build secondary, temperature scaled, model

- Training 4 models, implement ensemble to select best model

- Compile data, statistics, graphs

- Add section to report

### Build Report and Create Video

Assignee: Owen

Todo:

- Start building report with information gathered on base model

- Add templates for others to add information on their sections (monte carlo dropout, ensemble & temp scaling)

- Organize graphs and data for viewing ease and readability

- Ensure 6 page minimum requirement

- Create video and post to private youtube with link

- Update GitHub README

### Finish Report

Assignee: All

Todo:

- Introduction (All)

- Related Work (All)

- Dataset (Owen)

- Training Hardware (Hermes)

- Model with Monte-Carlo Confidence Evaluation + Graphs (Mike)

- MC Model Calibration (Hermes)

- Discussion (Hermes + Owen)

- Conclusion (All)

- Acknowledgment (All)